## Cover
TypeA Project
ServiceNow Utilization Guide(Progress Report and Furikaeri）
| Version | 0.1 | Date | 2023-03-22
| ※ | This document is based on ServiceNow specifications as of 2023/03.
It is expected that the DP ServiceNow will change in the future due to changes in ServiceNow specifications and the release of various tools.
Please check the following for the latest information.
Fujitsu Developers Platform Hub
https://fujitsu.sharepoint.com/sites/jp-dp-portal/SitePages/en/Home.aspx
© 2023 Fujitsu Limited

## At first
TypeA Project
ServiceNow Utilization Guide(Progress Report and Furikaeri）
At first
For project management of TypeA projects, use "ServiceNow (ITBM)" of "Fujitsu Developers Platform".
Fujitsu Developers Platform Hub
https://fujitsu.sharepoint.com/sites/jp-dp-portal/SitePages/en/Home.aspx
Fujitsu Developers Platform Guide
https://fujitsu.sharepoint.com/sites/jp-dp-portal/SitePages/en/guide.aspx
This document summarizes the information necessary for TypeA project management using ServiceNow (ITBM).
It is based on the "ServiceNow (ITBM) User guidelines" published on the above site.
(1)Purpose of this document
Regardless of the project, we will show the input policy and reporting perspective for progress reporting from a common perspective.
We aim to achieve the following goals:
1)Contribution to reduction of preparatory work costs by unified items and viewpoints
2)Contribution to improved reporting accuracy through evidence-based reporting
3)Contribution to time efficiency through progress meetings based on common perspectives
(2)Target audience
|  | ・ | JDU PM
|  | ・ | JDU developer
(3)Prerequisite
Before using the Fujitsu Developers Platform, be sure to access the above site and check the necessary documents.
|  | ・ | はじめに必ずお読みください
|  | ・ | ServiceNow(ITBM) 開発業務向け
|  | ・ | 情報資産取り扱いガイドライン
|  | ・ | All information has been registered to ServiceNow according to the "TypeA ServiceNow Utilization Guide (PM edition)
and TypeA ServiceNow Utilization Guide (Developer edition)".
|  | ・ | The information entered in ServiceNow is up-to-date

## Revision history
TypeA Project
ServiceNow Utilization Guide(Progress Report and Furikaeri）
Revision history
| Version | Contents | Person In charge | date
| 0.1 | Newly created (with education information) | Zhangyuan Li , Keiko Tsuno | 2023-03-22

## Table of Contents
TypeA Project
ServiceNow Utilization Guide(Progress Report and Furikaeri）
Table of Contents
How to Write Progress Reports
1. Project Information Input
2. Whole Progress Input
3.Progress Status_PS
3.Progress Status_PG
3.Progress Status_PT
4.Issue_5.QA
6. Man-hour Management Input
Reporting aspects of the progress report
Perspective_PS
Perspective_PG
Perspective_PT
Perspective_issue_QA
How to write a retrospective report
Preparing

## 1. Project Information Input
Table of Contents
1. Project Information Input
For the "1. Project Information" of each phase, enter the data according to the following procedure.
1.)Copy the Project plan information to "1. Project Information".
|  | 1 | Copy the necessary information from the project plan and project plan attachments.
|  |  | № | 項目名 | 入力値 | 備考
|  |  | 1 | プロジェクト名称/Project Name | Copy from Project Plan "1.1. プロジェクト概要/Project Overview".
|  |  | 2 | プロジェクト全体規模(KLOC)/Whole Scale(KLOC) | Copy from Project Plan "1.1. プロジェクト概要/Project Overview" * "別紙_01 Overview/Attachment _ 01 Overview".
|  |  | 3 | 作業内容/Work Discription | Copy from Project Plan "1.1. プロジェクト概要/Project Overview".
|  |  | 4 | 対象工程/Target Phase | Manually enter the phase to be reported.
|  |  | 5 | GDC開発規模(KLOC)/GDC Development Scale(KLOC) | Copy from Project Plan "1.1. プロジェクト概要/Project Overview". | Latest values must be measured and updated before starting the PG and PT phase.
|  |  | 6 | GDC要員数/GDC's Number of Members | Copy from Project Plan "1.2. プロジェクト体制と役割分担/Project structure and Division of roles * "別紙_02 体制と役割分担/Attachment _ 02 Structure and Division of Roles". | Enter the number of members excluding PM. (Include the Bridge member.)
■Status Report Input Image
236KLOC
12KLOC
【Project Plan】
  Restrictions and conditions of JDU development work

## 2. Whole Progress Input
Table of Contents
2. Overall Progress Input
The "2. Overall Progress" of each process follows the steps below to post information from the ServiceNow dashboard.
| Check on your dashboard |  |  |  |  | source
|  | 1 | Select “All” from the top menu. |  |  | ServiceNow_CommonUserGuide_Eng.pdf
|  | 2 | Enter “PJ Dashboard” in the filter of the menu, and select |  |  | 3.3.1 How to display the dashboard
Page-based, such as SS and PS：「PJ Dashboard (Document page base)」
When scale-based, such as PG and PT：「PJ Dashboard (Source code base)」
|  | 3 | The “PJ Dashboard” screen will be displayed. Select “Project”.
|  | 4 | Select "Select elements" and click "Clear All".
Previous checks may remain, so be sure to click "Clear All" before proceeding.
|  | 5 | Check the project of the process to be reported.
When checking the overall progress, check all projects in the same process.
Example: If there are "000000PJname_PS_AAA" and "000000PJname_PS_BBB", check both.
When checking each project (= function), check only the target project.
Example: If there are "000000PJname_PS_AAA" and "000000PJname_PS_BBB", check one of them.
|  | 6 | Click the "Apply" button.
|  | 7 | A summary screen for the selected project appears. Capture the summary screen and paste it in the "2. Overall progress input" column of the progress report.
* The red letters in the current value of the summary indicate an error. You can view the tab of the item in error and check the details.
3
4
5
6

## 3.Progress Status_PS
Table of Contents
3.Progress Status：PS Phase
In the PS process, we report mainly on the document creation status.
In "3. Progress" of the PS process, ServiceNow data is posted according to the following contents.
|  | Item Name |  | Value
|  | タスク(管理項目4)Task Management Item 4 |  | Function name = Project name
|  | ドキュメント率/Document rate(頁/KLOC) |  | 「F01M04A14_別紙_14 品質管理指標／Quality Management Index-value.xlsx」 PS 「ドキュメント率(頁/KLOC)/Document rate(Pages/KLOC)」の「中央値/Median」
|  | 計画規模/Planned scale （KLOC） |  | Planned scale（KLOC）
|  | ドキュメント頁数(計画値)/Number of document pages (plan) |  | Check the dashboard and enter the total number of "planned document pages". For details on how to check, see "Check on the Dashboard" below.
|  | 実績/Actual |  | Enter the following values. You can check the number of actual document pages on the dashboard. For details on how to check, see "Check on the Dashboard" below.
|  |  | 先週までの合計/cumulative total up to last week | Here are the totals for the previous week's report: 「先週までの合計/cumulative total up to last week」+「今週/This week」
|  |  | 今週/This week | Enter the number obtained by subtracting the above "cumulative total up to last week" from the "number of document pages".
Check on the dashboard
| 1 | Perform steps 1 to 6 on the "2. Overall progress input" sheet to display the dashboard screen.
| 2 | Click the number part of "Total number of document pages (results)".
| 3 | A list of "Estimated/Actual scale (Pages) management" will be displayed. Check the registered "Number of scheduled document page" and "Number of actual document page".
2
3

## 3.Progress Status_PG
Table of Contents
Progress Status：PG Phase
In the PS process, we report mainly on the scale creation status.
In "3. Progress" of the PG process, ServiceNow data is posted according to the following contents.
|  | Item Name |  |  | Value
|  | タスク(管理項目4)Task Management Item 4 |  |  | Function name = Project name
|  | 見積規模/Estimated Scale(KLOC) |  |  | Enter "1. Estimated development scale (ks)" in "Productivity (Planned) (ks/H)" on the dashboard. For details on how to check, see "Check on the Dashboard" below.
完了タスク数/The number of completed tasks
|  |  | 計画値/Plan |  | Enter the "Total tasks" of "Completion rate (Overall)" on the "Progress" tab of the dashboard. For details on how to check, see "Checking on the Dashboard" below.
|  |  | 実績/Actual | 先週までの合計 /cumulative total up to last week | The totals for the previous week's report: 「先週までの合計/cumulative total up to last week」+「今週/This week」
|  |  |  | 今週/This week | Enter the value obtained by subtracting the above "「先週までの合計/cumulative total up to last week」" from the "current number of completions" in the "completion rate (total)" on the "progress" tab of the dashboard.
|  | 実規規模(KLOC)Actual Scale |  |  | Enter "1. Actual development scale (ks)" in "Productivity (actual) (ks/H)" on the dashboard. For details on how to check, see "Check on the Dashboard" below.
Check on the dashboard
| 1 | Perform steps 1 to 6 on the "2. Overall progress input" sheet to display the dashboard screen.
| 2 | Click Progress tab.
| 3 | Check the "Completed item count" and "Total tasks" of "Completion rate (Overall)".
| 4 | Scroll to the bottom.
Check "1. Estimated development scale (ks)" in "Productivity (Planned) (ks/H)".
Check "1. Actual development scale (ks)" of "Productivity (Actual) (ks/H)".
2
In "planned value/Plan"
will post
"This week"
use for calculation
「見積規模/Estimated Scale(KLOC)」
「実規規模(KLOC)Actual Scale」

## 3.Progress Status_PT
Table of Contents
Progress Status：PT Phase
In the PT process, we report mainly on the test status of each program.
In "3. Progress" of the PT process, the ServiceNow data will be posted according to the following contents.
*We defined it as follows, but we would like to improve it if there is a more easy-to-understand reporting method.
|  | Item Name |  | Value
|  | タスク(管理項目4)Task Management Item 4 |  | Function name = Project name
|  | テスト完了率(全体) Test completion rate (Overall) |  | Check it on your dashboard. For details on how to check, see "Check on the Dashboard" below.
テスト完了数 現状値 Test completion - Current value
全テスト項目数 Total test items
|  | テスト完了率(時点) Test completion rate (point of time) |  | Check it on your dashboard. For details on how to check, see "Check on the Dashboard" below.
テスト完了数 現状値 Test completion Current value
全テスト項目数 Test completion current - Project value
"6. 障害/Bugs" of the PT process will post the data of ServiceNow according to the following contents.
|  | Item Name |  | Value
|  | open |  | Check with「■障害検出率(障害検出数/全開発規模(実績)(ks))」on the dashboard.For details on how to check, see "Check on the Dashboard" below.
|  |  | 前回までの合計 /Total up to the last time | In the "Failures list", check the number of occurrences with "Occurred date" up to last week.
|  |  | 今週 /this week | In the "Failures list", check the number of occurrences with "Occurred date" up to this week.
|  | close |  | Check it on your dashboard. For details on how to check, see "Check on the Dashboard" below.
|  |  | 前回までの合計 /Total up to the last time | In the "Failures list", check the number of occurrences with "Verification date" up to last week.
|  |  | 今週 /this week | In the "Failures list", check the number of occurrences with "Verification date" up to this week.
Check on the dashboard
| 1 | Perform steps 1 to 6 on the "2. Overall progress input" sheet to display the dashboard screen.
| 2 | Click Quality(Test) tab.
| 3 | Check the following items and post them to the progress report.
■テスト完了率(全体)/Test completion rate (Overall)
テスト完了数 現状値/Test completion - Current value
全テスト項目数/Total test items
■テスト完了率(時点)/Test completion rate (point of time)
テスト完了数 現状値/Test completion Current value
全テスト項目数/Test completion current - Project value
| 3 | Check the following items and post them to the progress report.
■障害検出率(障害検出数/全開発規模(実績)(ks))/Failure detection rate (Failures deteced/Total development scale (Actual)(ks))
Check the following in「障害一覧/Failure list」
|  | ・ | Number of dates with 「発生日/Occurred date」 up to lase week
|  | ・ | Number of dates where 「発生日/Occurred date」 is this week's date
|  | ・ | Number of dates where 「検証完了日/Verification actual date」 is up to last week
|  | ・ | Number of dates where 「検証完了日/Verification actual date」 is this week's date
2

## 4.Issue_5.QA
Table of Contents
4.Issue
5.QA
The number of "4. Issues" and "5. Q&A" for each process will be posted according to the following procedure.
Check domain scope first after login
If you join multiple project, you will be registered in multiple domains (project rooms) in ServiceNow. Please confirm that the domain scope is correct.
method
|  | 1 | Click on the right.
|  | 2 | Make sure the "Domain Scope" is correct.
|  | 3 | If a different domain scope was selected, select the correct domain scope.
View dashboard
| 1 | Select "All" from the top menu.
| 2 | Enter "PJ" in the menu filter, and select "PJ Dashboard (Document page base)" or
"PJ Dashboard (Source code base)" under "(New) PJ status Dashboard ITBM" ".You can choose either.
| 3 | The "Project status display" screen is displayed. Select "Program".
| 4 | Select "Select Elements".
| 5 | Click Clear All.
Previous checks may remain, so be sure to click "Clear All" before proceeding.
| 6 | Check the program of the process to be reported.
| 7 | Click the "Apply" button.
| 8 | A summary screen for the selected program appears. Click "Total".
| 9 | A list of "issue" is displayed.
The following items are not displayed by default. To display it, perform the operation of "Adding a Point heading item" described later.
Select free item 1 (Classfication) "Select free item 1 (Options)" "Created date and time" "Closed"
Select free item 2 (Classfication) "Select free item 2 (Options)"
| 10 | 「番号」の行で右クリックし、「エクスポート」、「Excel(.xlsx)」の順に選択します。
2
A list of issues is output in an Excel file.
|  | Item name |  |  | Value
|  | Short description |  |  | Lines with "QA" at the beginning are QA, lines without "QA" at the beginning are issues.
|  | Select free item 1 (Options) |  |  | Process name
|  | Created |  |  | The date the issue was opened.
|  | Closed |  |  | Date closed. If it is blank, it is open.
| 12 | Count each item.
|  | 12_1 | Sort by the process name of "Select free item 1 (Options)"
|  | 12_2 | For each process divided in 12_1, divide into those with "QA" in the writing characters of "Short description" and those without
|  | 12_3 | Count the number of lines created up to last week for each "Issue" and "QA" of each process divided by 12_2
|  | 12_4 | Count the number of rows created in the current week for each "Issue" and "QA" of each process divided by 12_2
|  | 12_5 | Count the number of lines closed by the date up to last week for each "Issue" and "QA" of each process divided by 12_2
|  | 12_6 | Count closed rows for this week's date for each "Issue" and "QA" for each process divided by 12_2
| 13 | Write down the numbers counted in step 12 on the sheet for each process in the progress report.
add items
Customize the issue list to display the following items:
Select free item 1 (Classfication) "Select free item 1 (Options)" "Created date and time" "Closed"
Select free item 2 (Classfication) "Select free item 2 (Options)"
List customizations are set per domain scope, so first make sure the domain scope is correct.
| 1 | Click on the upper right.
| 2 | Make sure the "Domain Scope" is correct.
| 3 | Click "(Customize list)".
| 4 | The Customize List Columns screen appears.
Select the following items from "Available" on the left and click the ">" button to move to the right.
選択する項目
Closed
Select free item 1 (Classfication)
Select free item 1 (Options)
Select free item 2 (Classfication)
Select free item 2 (Options)
Created
| 5 | In "Selected" on the right, use " " and " " to change the order as follows.
Select free item 1 (Classfication)
Select free item 1 (Options)
Created
Closed
Select free item 2 (Classfication)
Select free item 2 (Options)
| 6 | In "Selected" on the right, select the following 4 lines and click " " multiple times to move them under "Short description".
Select free item 1 (Classfication)
Select free item 1 (Options)
Created
Closed
| 7 | Click"OK"
7
6
5
3
4
8
10
12_3
12_4
12_5
12_6
12_3
12_4
12_5
12_6
1
3
4
5
6
7
1
2
3
2
1

## 6. Man-hour Management Input
Table of Contents
6. Man-hour Management Input
For the "6. Man-hour Management" of each phase, transfer the data according to the following procedure.
1.)Enter the daily plan in the progress report.
|  | 1 | Check the planning time during estimation.
■Example of estimation
|  | 2 | Enter scheduled time in the status report.
■Image for entering the plan information
|  | 3 | Update the Plan information according to the latest entity.
Days with expected uptime(Operation increase): Revise according to expected uptime
Days on which planned leave is expected: Adjust the planned time to "0".
*Do not change schedule for unexpected leaves or interruptions.
|  |  | ■ | Image of Modified Plan information
| 2.)"累計工数(先週まで)"に"今週の作業累計"の予定および実績数値を転記します。 | Transfer the Planned and Actual figures of "今週の作業累計/Total man-hour for this week" to "累計工数(先週まで)/Total man-hour (Until last week)".
■Before Transferring
■After Transferring
3.)Review and enter actual time in the ServiceNow Timecard.
Refer to the Timecard Confirmation sheet in the Service Now Usage Guide (PM version) for information on how to check timecards.
■Image after transferring man-hour
Check the expected work hours (H/d).
Reflect the planned leave schedule.
Enter the skill level of the contact member
Enter the plan for the operation increase
Enter the plan for the operation increase
(KLOC)
(KLOC)

## Perspective_PS
Table of Contents
Reporting Perspective : PS Phase
The reporting for the creation status of the documents will be mainly performed at the PS phase.
（1） Progress Status
The PS phase gives attention to the planned and actual status of the document creation and reports the progress status.
Use the Tophat for the basis of the numerical value item in the report and conduct reporting based on the objective numerical value and not on the reporter’s subjective opinion.
The reporting perspectives are shown below.
ア. Tasks that proceed according to plan
Even in cases where the tasks proceed as planned, record the existing risks that influence the future prospects and progress and worrying factors such as matters of concerns.
イ. Tasks with delays
Conduct a status analysis from the hearings with the personnel and output report of the Tophat and clarify the root cause.
List the countermeasures and basis, need for rescheduling and importance of the horizontal development, status of the horizontal development, and future prospects.
Ex: Image of the progress report in case of delay in the design document creation
（ｱ） Clarify and describe the delay status, cause analysis of the delay, and basis for the determination of the root cause.
The PM should identify the cause of the delayed task and report the basis for its identification.
Also, delayed tasks should report the “Degree of impact on the overall progress”.
Examples of the delay cause are shown below.
A. Problems on the estimation (The original schedule has increased.)
・Was it a highly accurate estimate?
・Is there a lot of uncertain factors?
・Are there problems with the work process?
・Are Q&As being raised frequently?
B. Problem concerning persons (Low productivity)
・Did a skill mismatch occur?
・Did the person in charge have multiple ongoing tasks or projects?
・Were they on leave for many days which resulted in less working hours?
・Was the leader’s management ability lacking? Was leadership being manifested?
・Were there no impacts to their supposed performance due to poor physical condition or declining motivation?
C. Rework and waiting for tasks due to the impact of input documents and other team tasks
・Has the input document shown in the project plan document been received? Also, is its quality ensured?
・Were the issues not solved by the desired due date?
・Were the Q&As to the customers and other teams not have been resolved by the desired due date?
・Are reviews and meetings not being held as scheduled?
（ｲ） Include a recovery plan
The PM should investigate countermeasures for the identified root cause and report on how to conduct the recovery.
Also, make sure to report the "Determination for the importance of the horizontal development".
Examples for the recovery plan are shown below.
A. Increase the working hours of the current personnel
Pay attention to the risks for the productivity deterioration and motivation due to excessive overtime work.
Also, be aware of the problem solving cannot be done depending on the delayed no. of days.
it should be recognized that the problem cannot be solved depending on the number of days of delay.
[Example]: Delay for the scheduled working time of 8 hours/1 day
1 day of delay: Recovery is possible in 4 days with 2 hours of overtime (25% work increase).
Or, by working for 1 day (8H) on a holiday.
2 days of delay: Recovery is possible in 4 days with 3.4 hours of overtime (40% work increase).
Recovery is possible with 2 hours of overtime (25% work increase) and by working for 1 day (8H) on a holiday.
3 days of delay: Recovery until the following week is difficult due to the increase of work. Succeeding tasks will certainly be affected.
B. Adding of personnel
Take into consideration that even in adding external resources in the middle of the project, recovery will not be done easily.
Adding of personnel is effective when there is time for the succeeding phases and succeeding development.
The important point is for the kinds of documents used for development are prepared.
C. Change of personnel and review of duties
Consider changing the personnel if their skills are lacking or the skills they possess are different from the skills required by the project.
※However, make sure not to carelessly decide and also confirm the skill plan and cooperate with the person in charge higher than the PM level for the JDU side.
By changing the person in charge in the middle of a project, a substitute that can take over the tasks will be required. Also, take into consideration that the productivity will temporary decline and there is a risk of progress deterioration.
D. Reduce the scale of operations
Consider measures to reduce the scale of operations and to prevent an increase in the man-hours by means of the "Promotion of standardization" and "Framework deployment".
※It should be noted that this is a reduction in the scale of operations by improving the work efficiency and not the reduction of the scale which was originally assumed (agreed upon).
E. Advanced precautionary measures ※Measures in anticipation of delays.
Set a checkpoint date, determine who, to whom, how is the situation, and what needs to be confirmed, and confirm the status.
F. Other measures (Ways to the increase motivation)
When the cause is the motivation of personnel, come up with ways to add work-life balance such as forcing employees to return home at once and prohibiting them from working on holidays.
（ｳ） Provide the rationale for the recovery plans
A recovery plan must include the rationale and recovery period. The rationale and recovery period is described with numerical values (Data) and not with the PM’s intuition, and reports objective facts.
（ｴ） State the implementation status of the recovery plan
State whether the tasks under the recovery plan is proceeding as planned and if there are new problems are generating.
In case a new problem has generated, verify and report the validity of the current recovery plan in addition to the root cause analysis.
ウ. Tasks with plans that will largely change
Clarify the cause which generated discrepancies with the plan and list the countermeasures and basis, need for rescheduling and importance of the horizontal development, status of the horizontal development, and future prospects.
Ex: Image of the planned changes
（ｱ） Identify and describe the cause of the discrepancies and the basis for determining the root cause.
The PM should identify the cause of the discrepancies and report the basis for its identification.
Also, report the “Importance of the horizontal development” and “Degree of impact on the overall progress”.
For the analysis perspective, refer to "2.1. （1）.イ.（ｱ） Clarify and describe the delayed status, cause analysis of the delay, and basis for the determination of the root cause".
（ｲ） Describe the rescheduling or recovery scheduling decision.
Changes in the schedule, as a general rule, requires the cause for discrepancies to be clear and the planned completion date of the phase to be kept the same. When changes are determined to be required, the “Schedule after changes” must be created in addition to the reason for the decision on the scheduling changes.
（2） Issues
Refer to “Perspective_issue_QA”
（3） Q & A
Refer to “Perspective_issue_QA”

## Perspective_PG
Table of Contents
Reporting Perspective : PG Phase
The reporting for the creation status of the classes will be mainly performed at the PS phase.
（1） Progress Status
The PG phase gives attention to the no. of programs and reports the progress status. Use the Tophat for the basis of the numerical value item in the report and conduct reporting based on the objective numerical value and not on the reporter’s subjective opinion.
Every reporting perspective of the progress status for the work task is shown below.
ア. Tasks that proceed according to plan
Refer to "2.1.（1）.ア. Tasks that proceed according to plan”
イ. Tasks with delays
Conduct a status analysis from the hearings with the personnel and output report of the Tophat and clarify the root cause.
During the hearing, check the actual task (program creation status and updated status, etc.) and confirm if there are no differences.
List the countermeasures and basis, need for rescheduling and importance of the horizontal development, status of the horizontal development, and future prospects.
Ex: Image of the implementation delay
（ｱ） Clarify and describe the delay status, cause analysis of the delay, and basis for the determination of the root cause.
The PM should identify the cause of the delayed task and report the basis for its identification.
Also, delayed tasks should report the “Degree of impact on the overall progress” and “Degree of impact to the other subsystems and other teams”.
Examples of the root causes aside from the “2.1.（1）.イ. （ｱ） Clarify and describe the delayed status, cause analysis of the delay, and basis for the determination of the root cause” are shown below.
A. Environment problems (Lack of verification and preparation for the development environment)
・Is development environment the same as the one described in the project plan?
・Has the connection of the development environment and task verification been implemented?
・Have the various applications (applicable or non-applicable determination or act of approval) been completed?
（ｲ） Include a recovery plan
Refer to "2.1.（1）.イ. （ｲ） Include a recovery plan” for the description perspective.
ウ. Task with an implementation scale that will largely change
Clarify the cause of the scale changes and list the countermeasures and basis, need for rescheduling and importance of the horizontal development, status of the horizontal development, and future prospects.
Ex Image of the changes in the implementation scale
Description perspectives asides from the "2.1.（1）.ウ. Tasks with plans that will largely change" are shown below.
（ｱ） Identify and describe the cause of the discrepancies and the basis for determining the root cause
Refer to “2.1.（1）.イ.（ｱ） Clarify and describe the delayed status, cause analysis of the delay, and basis for the determination of the root cause” for the description perspective.
（ｲ） Describe the rescheduling or recovery scheduling decision
Refer to “2.1.（1）.イ. （ｲ） Describe the rescheduling or recovery scheduling decision” for the description perspective.
（2） Issues
Refer to “Perspective_issue_QA”
（3） Q & A
Refer to “Perspective_issue_QA”

## Perspective_PT
Table of Contents
Reporting Perspective : PT Phase
The reporting for the test status of the program units will mainly be performed at the PT phase.
（1） Progress Status
The PT phase reports the occurrence and correspondence status of the non-failures and not the implementation status of the tests.
Use the Tophat for the basis of the numerical value item in the report and conduct reporting based on the objective numerical value and not on the reporter’s subjective opinion.
The description perspective of the progress status for the work tasks are shown below.
ア. Tasks that proceed according to plan
Refer to "2.1.（1）.ア. Tasks that proceed according to plan”.
イ. Tasks with delays
Conduct a status analysis from the hearings with the personnel and output report of the Tophat and clarify the root cause.
During the hearing, check the actual task (program creation status and updated status, etc.) and confirm if there are no differences.
List the countermeasures and basis, need for rescheduling and importance of the horizontal development, status of the horizontal development, and future prospects.
Ex: Image of the test delay
（ｱ） Clarify and describe the delay status, cause analysis of the delay, and basis for the determination of the root cause.
The PM should identify the cause of the delayed tasks and report the basis for its identification.
Also, delayed tasks should report the “Degree of impact on the overall progress” and “Degree of impact to the other subsystems and other teams”.
Examples of the root causes asides from the “2.1.（1）.イ. （ｱ） Clarify and describe the delayed status, cause analysis of the delay, and basis for the determination of the root cause” and “2.2.（1）イ. （ｱ） Clarify and describe the delayed status, cause analysis of the delay, and basis for the determination of the root cause” are shown below.
（ｲ） Include a recovery plan
Refer to "2.1.（1）.イ. （ｲ） Include a recovery plan” for the description perspective.
ウ. Failed tasks * Report failures to be issued as (FAILURE).
Analyze the occurrence trend of the defects and report the results.
Confirm the validity of the data (Concept of the test items, cause phase of the defect, classification of the cause category and etc.) during the analysis.
Ex: Image of the defect occurrence
（ｱ） Perform an analysis of the defect occurrence status and list the analysis results.
Examples for the perspectives of the analysis are shown below.
・Is the actual value for the quality index value within the acceptable range?
・Is there a trend for the content of the defects?
・Is the comprehensiveness of the test enough?
・Are the no. of defects being converged within the phase?
・Are there too many defects to be extracted at the previous phase?
・Are there any defects caused by the work procedure?
・Are there any defects that depended on the developer (Skills)?
・Is there any problem with the quality data itself?
（2） Issues
Refer to “Perspective_issue_QA”
（3） Q & A
Refer to “Perspective_issue_QA”

## Perspective_issue_QA
Table of Contents
Reporting Perspective： Issue and Q & A
（1） Issues
Issues reports the remaining issues up until now especially those which have not been resolved and are just left behind.
Also, it also analyzes the new issues that generated during the progress reporting week and reports critical issues.
ア. Issues left over from the previous week
From those issues that should have been resolved at reporting week, list the issue no. of those that have yet to be resolved.
In case the cause on why there are no progresses with the issue is clear, then list the cause.
※Status of the issue (When, who, what, and what are the plan of actions decided to be done?) should be made clear.
※Details of the issues can be confirmed at the Tophat so there is no need to record it.
イ. New issues that generated during the reporting week
From those issues that have newly generated, list the issue no. of those with a high level of priority (high level of urgency).
※Status of the issue (When, who, what, and what are the plan of actions decided to be done?) should be made clear.
※Details of the issues can be confirmed at the Tophat so there is no need to record it.
ウ. Trends in the issues
Conduct an analysis on the issues that have generated, analyze if there are trends and problems in the processes, input documents, interfaces, people in charge, collaboration with other teams, etc., and describe the results.
| ※ | When specific trends and risks have become clear, set up another meeting separate from the progress meeting and devise a solution.
（2） Q & A
The Q & A reports the Q & As that is past the response due date and those that have a response due date during the reporting week.
Also, it analyzes and reports the high-level priority Q&A out of the Q & As that have newly generated during the reporting week.
ア. Q&As past the response due date
List the Q&A no. of those past the response due date.
イ. Q&As that are due on the reporting week
List the Q&As with a response due date the reporting week.
ウ. Q & A that newly generated at the reporting week
From the Q&As which have newly generated, list the Q&A no. of those with a high level of priority (high level of urgency).
エ. Trends in the Q & A
Conduct an analysis of the Q & A that generated, analyze if there are no problems for the Q & A occurrence trend and response time, quality of the questions and answers, and describe the results.